## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | R | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | OnlineWallet:001 | Design Documentation for Backend application | Sreenath | Sohaib | Average | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 22 hrs | Design is fullfilled agaist Business requirement
| 2 | Standard document |  | OnlineWallet:002 | Test Plan | Sreenath | Sohaib |  | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 8 hrs | Check the test case is fullfiled with user accepance criteria document
2 | 3 | Standard document | High | OnlineWallet:003 | Bootstrapping the project | Sreenath | Sohaib | Simple | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 4 hrs | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
3 | 4 | Work session | High | OnlineWallet:004 | Entity Class and TableDEsign and Populating the data | Sreenath | Sohaib | Complex | Low |  | RD:Business Requirement Doc | Functional |  |  |  |  | 8 hrs | Checking against the Table design in RD
4 | 5 | Work session | High | OnlineWallet:005 | Signing in: basic details to be filled by the user | Sreenath | Sohaib | Average | Low |  | RD:Business Requirement Doc | Functional |  |  |  |  | 10 hrs | TC_Service_01,TC_DAO_01, TC_UI_01
5 | 6 | Work session | High | OnlineWallet:006 | Logging in: email id and password required | Sreenath | Sohaib | Complex | Low |  | RD:Business Requirement Doc | Functional |  |  |  |  | 16 hrs | TC_Service_02,TC_DAO_02, TC_UI_03
6 | 7 | Work session | High | OnlineWallet:007 | Adding the money from bank account to the wallet | Sreenath | Sohaib | Simple | High |  |  | Functional |  |  |  |  | 12 hrs
7 | 8 | Work session | High | OnlineWallet:008 | Sending the money to the other wallet account user | Sreenath | Sohaib | Complex | High |  |  | Functional |  |  |  |  | 21 hrs
8 | 9 | Work session | High | OnlineWallet:009 | Passbook to show the amount in the wallet and transaction details | Sreenath | Sohaib | Complex | High |  |  | Functional |  |  |  |  | 15 hrs
9 | 10 | Work session | High | OnlineWallet:010 | Check balance to check the amount | Sreenath | Sohaib | Simple | Low |  |  | Functional |  |  |  |  | 8 hrs
10 | 11 | Work session | High | OnlineWallet:011 | Profile of the user containing basic details | Sreenath | Sohaib | Average | High |  |  | Functional |  |  |  |  | 12 hrs
12 | 13 | Work session | Low | OnlineWallet:012 | Admin Control methods | Sreenath | Sohaib | Complex | High |  |  | Functional |  |  |  |  | 20 hrs
Sprint 2 | Sprint 2
15 | 16 | Standard document | High | OnlineWallet:013 | Design Documentation fo Angular application | Sreenath | Sohaib | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional
| 17 | Standard document | High | OnlineWallet:014 | Test Plan | Sreenath | Sohaib |  | Low |  |  | Non Functional
16 | 18 | Work session | High | OnlineWallet:015 | Design login page | Sreenath | Sohaib | Complex | High |  |  | Functional |  |  |  |  | 15 hrs
17 | 19 | Work session | High | OnlineWallet:016 | Design signup page | Sreenath | Sohaib | Simple | Medium |  |  | Functional |  |  |  |  | 10 hrs
19 | 21 | Work session | Low | OnlineWallet:017 | Design Admin login page | Sreenath | Sohaib | Complex | High |  |  | Functional |  |  |  |  | 15 hrs
20 | 22 | Work session | Low | OnlineWallet:018 | Design Admin control page | Sreenath | Sohaib | Complex | High |  |  | Functional |  |  |  |  | 20 hrs
21 | 23 | Work session | Low | OnlineWallet:019 | Designnig the Home page | Sreenath | Sohaib | Simple | Low |  |  | Functional |  |  |  |  | 5 hrs
22 | 24 | Work session | High | OnlineWallet:020 | Creating Add money page | Sreenath | Sohaib | Simple | High |  |  | Functional |  |  |  |  | 6 hrs
23 | 25 | Work session | High | OnlineWallet:021 | Creating a interface page for adding money from Bank | Sreenath | Sohaib | Complex | High |  |  | Functional |  |  |  |  | 15 hrs
24 | 26 | Work session | High | OnlineWallet:022 | Creating a Transfer Money page | Sreenath | Sohaib | Average | High |  |  | Functional |  |  |  |  | 8 hrs
25 | 27 | Work session | High | OnlineWallet:023 | Creating Show Balance page | Sreenath | Sohaib | Simple | Low |  |  | Functional |  |  |  |  | 6 hrs
26 | 28 | Work session | High | OnlineWallet:024 | Creating Profile page | Sreenath | Sohaib | Complex | High |  |  | Functional |  |  |  |  | 12 hrs
27 | 29 | Work session | High | OnlineWallet:025 | Creating Transaction history page | Sreenath | Sohaib | Simple | Medium |  |  | Functional |  |  |  |  | 8 hrs
28 | 30
29 | 31
30 | 32
33
31 | 34
32 | 35
33 | 36
34 | 37
35 | 38
36 | 39
37 | 40
38 | 41
39 | 42
40 | 43
41 | 44
42 | 45
43 | 46
44 | 47
45 | 48
46 | 49
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.
Note on A3: This column is used to Link back to the Full MoSCoW list for the project (RD.045 sheet).
Note on B3: This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog
Note on C3: This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.).
Note on D3: Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have
Note on E3: Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW.
Note on F3: Brief description of the requirements necessary to fulfill the objective
Note on G3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on H3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on I3: Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex
Note on J3: Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low).
Note on K3: Used if reference is needed to another work product that provides further detail of the requirement. Examples include RA.027 Candidate Business Rules, RA.090 Reporting Fit Analysis, RA.027 Use Case Details, RD.070 Audit and Control Requirements), DS.030 Application Set-up Documents.
Note on L3: Column to document the originating process where the process is defined and necessary. For example, a process that originates from either Current Process Model [RD.030] or Future Process Model [RD.011].
Note on M3: Defines whether the User Story is Functional, Non-Functional or Technical type.
Note on N3: Column provides linkage to primary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on O3: Column provides linkage to secondary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on P3: Use column for supporting comments.
Note on Q3: Column for defining the agreed upon acceptance criteria
Note on R3: Description of the condition(s) that indicate the requirement has been satisfied.
Note on S3: This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied.
Note on T3: This column is used to provide supporting information, such as changes to the original requirement.

## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
15 | OnlineWallet: 015 | 1 | Wireframes and story boarding for each task | Aishwarya | 2020-04-27 | 2 hrs | 1 hr
|  | 2 | Routing Url List | Aishwarya | 2020-04-27 | 2 hrs | 2 hrs
|  | 4 | Angular service | Sharon | 2020-04-27 | 3 hrs | 2 hrs
|  | 5 | Components details | Sharon | 2020-04-27 | 2 hrs | 3 hrs
|  | 6 | Detail about the security | Sohaib | 2020-04-27 | 3 hrs | 2 hrs
16 | OnlineWallet: 016 | 1 | Designin Login Page | Sohaib | 2020-04-28 | 4 hrs | 3 hrs | Completed | 4 hrs
|  | 2 | Component sends the email and pasword to user service | Sohaib | 2020-04-28 | 5 hrs | 4 hrs | Completed | 7 hrs
|  | 3 | Userservice class confirms the user through backend | Sohaib | 2020-04-28 | 6 hrs | 5 hrs | Completed | 6 hrs
17 | OnlineWallet: 017 | 1 | Design a signup form that captures the details of users | Sohaib | 2020-04-27 | 3 hrs | 4 hrs | Completed | 6 hrs
|  | 2 | Component sends the details to service | Sohaib | 2020-04-27 | 3 hrs | 3 hrs | Completed | 5 hrs
|  | 3 | Angular service make the webservice call and get the userId after which user can log in | Sohaib | 2020-04-27 | 3 hrs | 3 hrs | Completed | 3 hrs
18 | OnlineWallet: 018 | 1 | Designin Admin Login Page | Sohaib | 2020-05-01 | 4 hrs | 3 hrs | Completed | 4 hrs
|  | 2 | Component sends the email and pasword to user service | Sohaib | 2020-05-01 | 5 hrs | 4 hrs | Completed | 7 hrs
|  | 3 | Userservice class confirms the admin through backend | Sohaib | 2020-05-01 | 6 hrs | 5 hrs | Completed | 6 hrs
19 | OnlineWallet: 019 | 1 | Designning a Admin control page which can manipulate the user details | Sohaib | 2020-05-01 | 10 hrs | 10 hrs | Completed | 12 hrs
|  | 2 | control component executes methods like display, delete, update etc. | Sohaib | 2020-05-01 | 15 hrs | 12 hrs | Completed | 15 hrs
|  | 3 | Service fetches the data through wireframing | Sohaib | 2020-05-01 | 8 hrs | 6 hrs | Completed | 8 hrs
20 | OnlineWallet: 020 | 1 | Design a home page which will have user functionalites | Sohaib | 2020-05-01 | 3 hrs | 3 hrs | Completed | 4 hs
|  | 2 | control component is having logout component | Sohaib | 2020-05-01 | 2hrs | 2 hrs | Completed | 2 hrs
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.

## Sprint Backlog 1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate (in hours) | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | OnlineWallet:001 | 1 | Entity Class Design | Sharon | 2020-02-14 | 4 | 2 |  | 3
|  | 2 | Table Design | Sharon | 2020-02-14 | 2 | 2 |  | 2
|  | 3 | Application Architecture | Sohaib | 2020-02-14 | 2 | 1 |  | 2
|  | 4 | Use case diagram | Aishwarya | 2020-02-14 | 2 | 2 |  | 3
|  | 5 | Sequence Diagram | Aishwarya | 2020-02-14 | 4 | 3 |  | 3
|  | 6 | Each use case detail description | Aishwarya | 2020-02-14 | 4 | 4 |  | 5
|  | 7 | Class Layer diagram | Sohaib | 2020-02-14 | 1 | 2 |  | 2
|  | 8 | Class Diagram | Sharon | 2020-02-14 | 2 | 2 |  | 3
|  | 9 | Webservice URL Details | Sohaib | 2020-04-14 | 1 | 1 |  | 1
2 | OnlineWallet:002 | 1 | Table Design | Sharon | 2020-04-17 | 2 | 2 |  | 2
|  | 2 | Application Architecture | Sohaib | 2020-04-17 | 2 | 1 |  | 2
|  | 3 | Use case diagram | Aishwarya | 2020-04-17 | 2 | 2 |  | 3
3 | OnlineWallet:003 | 1 | Creating a Spring boot starter project | Aishwarya | 2020-04-17 | 2 | 1 | Completed | 1
|  | 2 | Adding dependencies in Pom.xml and initializing it | Sohaib | 2020-04-17 | 1 | 1 | Completed | 1
|  | 3 | Adding server, jpa properties in application.properties | Sharon | 2020-04-17 | 2 | 1 | Completed | 2
4 | OnlineWallet:004 | 1 | Entity Class Design | Sharon | 2020-04-17 | 4 | 2 | Completed | 3
|  | 2 | Check tables are populated in DB | Sohaib | 2020-04-20 | 3 | 2 | Completed | 3
|  | 3 | Populate the Data | Aishwarya | 2020-04-20 | 3 | 4 | Completed | 3
5 | OnlineWallet:005 | 1 | Signup method which will take the user data entered from user in frontend | Sohaib | 2020-04-17 | 3 | 2 | Completed | 2
|  | 2 | Rest controller method to take the details in list form also containig the url with posmapping anotation | Sohaib | 2020-04-17 | 2 | 3 | Completed | 3
|  | 3 | Service method check the data wheather it is correct or not otherise throw exception | Sohaib | 2020-04-17 | 3 | 4 | Completed | 4
|  | 4 | Dao method contains the entitymanager which persist the data in database | Sohaib | 2020-04-17 | 3 | 4 | Completed | 5
6 | OnlineWallet:006 | 1 | Login method which will conduct the login criteria by taking data from user | Sohaib | 2020-04-21 | 5 | 7 | Completed | 15
|  | 2 | Rest Controller method to take the details and also containig the url with posmapping anotation | Sohaib | 2020-04-21 | 2 | 3 | Completed | 5
|  | 3 | Service method check the data wheather it is correct or not by comparing it from database otherise throw exception | Sohaib | 2020-04-21 | 3 | 3 | Completed | 6
|  | 4 | Dao method contains the entitymanager which will take help from jpa query to take the list of the users | Sohaib | 2020-04-21 | 2 | 4 | Completed | 6
7 | OnlineWallet:007 | 1 | Admin control methods to administer the accounts | Sohaib | 2020-04-24 | 9 | 14 | Completed | 15
|  | 2 | Rest Controller method to link the work of service with help of anotations | Sohaib | 2020-04-24 | 4 | 7 | Completed | 5
|  | 3 | Service method containing different methods to manage the project form admin side | Sohaib | 2020-04-24 | 5 | 6 | Completed | 4
|  | 4 | Dao method helps us in query building and various other tasks | Sohaib | 2020-04-24 | 3 | 6 | Completed | 6
8 | Online Wallet:008 | 1 | Add Money method which will enable users to add money to their Wallet | Aishwarya | 2020-04-20 | 3 | 1.5 | Completed | 2
|  | 2 | Rest Controller method to take the details and also containig the url with posmapping anotation | Aishwarya | 2020-04-20 | 2 | 2 | Completed | 2.5
|  | 3 | Service method check the data wheather it is correct or not by comparing it from database otherise throw exception | Aishwarya | 2020-04-21 | 2 | 1.5 | Completed | 3
|  | 4 | Dao method contains the entitymanager which will take help from jpa query to take the list of the users | Aishwarya | 2020-04-21 | 1 | 1.5 | Completed | 2
9 | Online Wallet:009 | 1 | Send Money method which will help users to transfer funds from one wallet account to another | Aishwarya | 2020-04-20 | 3 | 1.5 | Completed | 2.5
|  | 2 | Rest Controller method to take the details and also containig the url with posmapping anotation | Aishwarya | 2020-04-22 | 2 | 2 | Completed | 2
|  | 3 | Service method check the data wheather it is correct or not by comparing it from database otherise throw exception | Aishwarya | 2020-04-22 | 2 | 2.5 | Completed | 3
|  | 4 | Dao method contains the entitymanager which will take help from jpa query to take the list of the users | Aishwarya | 2020-04-22 | 1 | 1.5 | Completed | 2
10 | OnlineWallet:010 | 1 | showallusers method which will take the user data entered from user in frontend | Sharon | 2020-04-20 | 3 | 1.5 | Completed | 4
|  | 2 | Rest controller method to take the details in list form also containig the url with posmapping anotation | Sharon | 2020-04-21 | 2 | 2 | Completed | 3
|  | 3 | Service method check the data wheather it is correct or not otherise throw exception | Sharon | 2020-04-21 | 2 | 1.5 | Completed | 3
|  | 4 | Dao method contains the entitymanager which persist the data in database | Sharon | 2020-04-22 | 1 | 1.5 | Completed | 2
11 | OnlineWallet:011 | 1 | showprofile method which will show the profiledata from user | Sharon | 2020-04-22 | 5 | 7 | Completed | 15
|  | 2 | Rest Controller method to take the details and also containig the url with posmapping anotation | Sharon | 2020-04-23 | 2 | 3 | Completed | 5
|  | 3 | Service method check the data wheather it is correct or not by comparing it from database otherise throw exception | Sharon | 2020-04-24 | 3 | 3 | Completed | 6
|  | 4 | Dao method contains the entitymanager which will take help from jpa query to take the list of the users | Sharon | 2020-04-24 | 2 | 4 | Completed | 6
12 | Online Wallet:012 | 1 | updateprofile method which will enable users to update the profile | Sharon | 2020-04-20 | 3 | 2 | Completed | 2
|  | 2 | Rest Controller method to take the details and also containig the url with posmapping anotation | Sharon | 2020-04-20 | 2 | 3 | Completed | 3
|  | 3 | Service method check the data wheather it is correct or not by comparing it from database otherise throw exception | Sharon | 2020-04-21 | 3 | 4 | Completed | 4
|  | 4 | Dao method contains the entitymanager which will take help from jpa query to take the list of the users | Sharon | 2020-04-21 | 3 | 4 | Completed | 5
13 | OnlineWallet: 013 | 1 | Show Balance method which helps users to check the balance in their wallet account. | Sharon | 2020-04-20 | 3 | 1.5 | Completed | 4
|  | 2 | Rest Controller method to take the details and also containig the url with posmapping anotation | Sharon | 2020-04-23 | 2 | 2 | Completed | 3
|  | 3 | Service method check the data wheather it is correct or not by comparing it from database otherise throw exception | Sharon | 2020-04-23 | 2 | 1.5 | Completed | 2
|  | 4 | Dao method contains the entitymanager which will take help from jpa query to take the list of the users | Sharon | 2020-04-24 | 1 | 1.5 | Completed | 3
14 | OnlineWallet: 014 | 1 | Selectdate method which helps users to see only the needed transaction details | Sharon | 2020-04-23 | 3 | 1.5 | Completed | 4
|  | 2 | Rest Controller method to take the details and also containig the url with posmapping anotation | Sharon | 2020-04-23 | 2 | 2 | Completed | 3
|  | 3 | Service method check the data wheather it is correct or not by comparing it from database otherise throw exception | Sharon | 2020-04-24 | 2 | 1 | Completed | 2
|  | 4 | Dao method contains the entitymanager which will take help from jpa query to take the list of the users | Sharon | 2020-04-24 | 1 | 1.5 | Completed | 2
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.